## Leveling sheet
Bid Leveling Sheet
Free template from ArcSpecs · arcspecs.com/bid-leveling-guide
Project
Trade / package
Scope item | Sheet / spec ref | Sub A | Sub B | Sub C | Sub D
Base bid as submitted
Plug total (your numbers for missing scope)
Leveled total
Over the leveled low by
Rank (1 = true low)
Yellow cells with blue text are yours to fill in. Pick a status in each sub's left column. Type your plug number beside anything Missing, Excluded or Not stated. White and gray totals calculate themselves.

## Example
Bid Leveling Sheet
Free template from ArcSpecs · arcspecs.com/bid-leveling-guide
Project | Sample tenant build-out
Trade / package | 09 21 16 · Drywall & framing
Scope item | Sheet / spec ref | Sub A | Sub B |  | Sub C |  | Sub D
Base bid as submitted |  | 184200 | 162750 |  | 171900
Metal stud framing | A-201 | Incl. | Incl. |  | Incl.
GWB hang, tape & finish | 09 21 16 · 3.4 | Incl. | Incl. |  | Incl.
Shaftwall at elevator | A-501 · detail 4 | Incl. | Missing | 11800 | Incl.
Firestopping at rated walls | 07 84 00 | Incl. | Excluded | 6200 | Missing | 6200
Blocking for millwork | A-610 | Incl. | Missing | 3400 | Incl.
Deflection head track | 09 22 16 · 2.3 | Incl. | Incl. |  | Incl.
Plug total (your numbers for missing scope)
Leveled total
Over the leveled low by
Rank (1 = true low)
Yellow cells with blue text are yours to fill in. Pick a status in each sub's left column. Type your plug number beside anything Missing, Excluded or Not stated. White and gray totals calculate themselves.
Every project, company and dollar figure on this tab is made up to show how the sheet works.